## Sheet1
Code | Name | Description | Target | Verification indicator | Month | Associated WP | Associated tasks | Associated deliverables | Language | Channels | Feeds on activities/tasks - code | Lead partner | Role of lead partner | Lead researcher (TBD by lead partner)
A1 | PDEC & IPR | Production of PDEC & IPR | Deliverable produced | Deliverable | 4 | 6 | 6.1 | D6.1 | EN | Virtual forum (website) | - | USAL | Coordinate development of the PDEC & IPR, including this roadmap and SMART (specific, measurable, assigned, realistic and timely) indicators for all activities | C. Dionisio Pérez-Blanco
A2 | Business plan | Development of business plan | Deliverable produced | Deliverable | 37 | 6 | 6.2 | D6.5 | EN | Virtual forum (website), fora with key policymakers | T5.2-3 | ARPAE | Coordinate development of the business plan | Cinzia Alessandrini
A3 | Project brochure/leaflet 1 - EN | Substantiate why TAP are relevant for sustainable water resources management | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 4 | 6 | 6.3 | D6.1 | EN | Virtual forum, newsletter, twitter | T6.1 | ARPAE & USAL | Develop leaflet summarizing the project objectives and its relevance - adapted to stakeholders, mainly policy makers - and disseminate widely at a EU label and across potential legacy labs | Cinzia Alessandrini & C. Dionisio Pérez-Blanco
A4 | Project brochure/leaflet 2 - IT | Substantiate why TAP are relevant for sustainable water resources management | 40+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 6 | 6 | 6.3 | D6.1 | IT | Virtual forum, newsletter, twitter | T6.1 | ARPAE | Develop leaflet summarizing the project objectives and its relevance - adapted to stakeholders, mainly policy makers - and disseminate widely at lab and national level | Cinzia Alessandrini
A5 | Project brochure/leaflet 3 - ES | Substantiate why TAP are relevant for sustainable water resources management | 40+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 6 | 6 | 6.3 | D6.1 | ES | Virtual forum, newsletter, twitter | T6.1 | SEI | Develop leaflet summarizing the project objectives and its relevance - adapted to stakeholders, mainly policy makers - and disseminate widely at lab and national level | Tania Santos
A6 | Project brochure/leaflet 4 - IN | Substantiate why TAP are relevant for sustainable water resources management | 40+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 6 | 6 | 6.3 | D6.1 | IN/EN | Virtual forum, newsletter, twitter | T6.1 | IRAP | Develop leaflet summarizing the project objectives and its relevance - adapted to stakeholders, mainly policy makers - and disseminate widely at lab and national level | Dinesh Kumar
A7 | Project brochure/leaflet 5 - GR | Substantiate why TAP are relevant for sustainable water resources management | 40+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 6 | 6 | 6.3 | D6.1 | GR | Virtual forum, newsletter, twitter | T6.1 | KRI | Develop leaflet summarizing the project objectives and its relevance - adapted to stakeholders, mainly policy makers - and disseminate widely at lab and national level | Marinos Kritsotakis
A8 | Project brochure/leaflet 6 - LE | Substantiate why TAP are relevant for sustainable water resources management | 40+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 6 | 6 | 6.3 | D6.1 | AR | Virtual forum, newsletter, twitter | T6.1 | AUB | Develop leaflet summarizing the project objectives and its relevance - adapted to stakeholders, mainly policy makers - and disseminate widely at lab and national level | Hadi Jaafar
A9 | Project brochure/leaflet 7 - SK | Substantiate why TAP are relevant for sustainable water resources management | 40+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 6 | 6 | 6.3 | D6.1 | SK | Virtual forum, newsletter, twitter | T6.1 | SAZP | Develop leaflet summarizing the project objectives and its relevance - adapted to stakeholders, mainly policy makers - and disseminate widely at lab and national level | Radoslav Povazan
A10 | Policy brief - Stakeholder mapping and rules of engagement | Stakehodler oriented summary of a key deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 1 | 1.1, 1.4 | D1.1 and D1.2 | EN | Virtual forum, newsletter, twitter | D1.1 and D1.2 | CMCC, ARPAE | Deliverable leader to develop 1-pager (or less) summary for policymakers in EN - ARPAE to disseminate widely the materials at a EU level leveraging on our networks | Jaroslav Mysiak, Cinzia Alessandrini
A11 | Policy brief - white paper methods & models | Stakehodler oriented summary of a key deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 3 | 3.1 | D3.1 | EN | Virtual forum, newsletter, twitter | D3.1 | USAL, ARPAE | Deliverable leader to develop 1-pager (or less) summary for policymakers in EN - ARPAE to disseminate widely the materials at a EU level leveraging on our networks | C. Dionisio Pérez-Blanco
A12 | Policy brief - white paper monitoring & enforcement | Stakehodler oriented summary of a key deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 4 | 4.1 | D4.1 | EN | Virtual forum, newsletter, twitter | D4.1 | UoM, ARPAE | Deliverable leader to develop 1-pager (or less) summary for policymakers in EN - ARPAE to disseminate widely the materials at a EU level leveraging on our networks | Tim Foster
A13 | Policy brief - white paper scenarios | Stakehodler oriented summary of a key deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 4 | 4.2 | D4.2 | EN | Virtual forum, newsletter, twitter | D4.2 | CMCC, ARPAE | Deliverable leader to develop 1-pager (or less) summary for policymakers in EN - ARPAE to disseminate widely the materials at a EU level leveraging on our networks | Jaroslav Mysiak
A14 | Policy brief - white paper governance | Stakehodler oriented summary of a key deliverable | 80+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 5 | 5.1 | D5.1 | EN | Virtual forum, newsletter, twitter | D5.1 | USAL, ARPAE | Deliverable leader to develop 1-pager (or less) summary for policymakers in EN - ARPAE to disseminate widely the materials at a EU level leveraging on our networks | C. Dionisio Pérez-Blanco
A15 | Policy brief - white paper financing | Stakehodler oriented summary of a key deliverable | 60+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 19 | 5 | 5.2 | D5.2 | EN | Virtual forum, newsletter, twitter | D5.2 | CMCC, ARPAE | Deliverable leader to develop 1-pager (or less) summary for policymakers in EN - ARPAE to disseminate widely the materials at a EU level leveraging on our networks | Jaroslav Mysiak
A16 | Policy brief - modeling suite sourcebook | Sourcebook produced as part of a deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 17 | 3 | 3.1 | D3.2 | EN | Virtual forum, newsletter, twitter | D3.2 | ARPAE | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Cinzia Alessandrini
A17 | Policy brief - water accounting & impact assessment sourcebook | Sourcebook produced as part of a deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 19 | 4 | 4.1 | D4.4 | EN | Virtual forum, newsletter, twitter | D4.4 | ARPAE | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Cinzia Alessandrini
A18 | Policy brief - policy notebook | Notebook produced as deliverable | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 4 | 5.1-3 | D5.3 | EN | Virtual forum, newsletter, twitter | D5.3 | ARPAE | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Cinzia Alessandrini
A19 | Policy brief - scenarios database sourcebook | Sourcebook produced as part of a deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 37 | 4 | 4.2 | D4.5 | EN | Virtual forum, newsletter, twitter | D4.5 | ARPAE | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Cinzia Alessandrini
A20 | Policy brief - white paper methods & models | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 3 | 3.1 | D3.1 | IT | Virtual forum, newsletter, twitter | D3.1 | ARPAE | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A21 | Policy brief - white paper methods & models | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 3 | 3.1 | D3.1 | ES | Virtual forum, newsletter, twitter | D3.1 | UPV | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Adrià Rubio
A22 | Policy brief - white paper methods & models | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 3 | 3.1 | D3.1 | IN/EN | Virtual forum, newsletter, twitter | D3.1 | IRAP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A23 | Policy brief - white paper methods & models | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 3 | 3.1 | D3.1 | GR | Virtual forum, newsletter, twitter | D3.1 | KRI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A24 | Policy brief - white paper methods & models | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 3 | 3.1 | D3.1 | AR | Virtual forum, newsletter, twitter | D3.1 | AUB | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A25 | Policy brief - white paper methods & models | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 3 | 3.1 | D3.1 | SK | Virtual forum, newsletter, twitter | D3.1 | SAZP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A26 | Policy brief - Stakeholder mapping and rules of engagement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 1 | 1.1, 1.4 | D1.1 and D1.2 | IT | Virtual forum, newsletter, twitter | D1.1 and D1.2 | ARPAE | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A27 | Policy brief - Stakeholder mapping and rules of engagement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 1 | 1.1, 1.4 | D1.1 and D1.2 | ES | Virtual forum, newsletter, twitter | D1.1 and D1.2 | SEI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Tania Santos
A28 | Policy brief - Stakeholder mapping and rules of engagement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 1 | 1.1, 1.4 | D1.1 and D1.2 | IN/EN | Virtual forum, newsletter, twitter | D1.1 and D1.2 | IRAP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A29 | Policy brief - Stakeholder mapping and rules of engagement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 1 | 1.1, 1.4 | D1.1 and D1.2 | GR | Virtual forum, newsletter, twitter | D1.1 and D1.2 | KRI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A30 | Policy brief - Stakeholder mapping and rules of engagement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 1 | 1.1, 1.4 | D1.1 and D1.2 | AR | Virtual forum, newsletter, twitter | D1.1 and D1.2 | AUB | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A31 | Policy brief - Stakeholder mapping and rules of engagement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 1 | 1.1, 1.4 | D1.1 and D1.2 | SK | Virtual forum, newsletter, twitter | D1.1 and D1.2 | SAZP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A32 | Policy brief - white paper monitoring & enforcement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.1 | D4.1 | IT | Virtual forum, newsletter, twitter | D4.1 | ARPAE | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A33 | Policy brief - white paper monitoring & enforcement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.1 | D4.1 | ES | Virtual forum, newsletter, twitter | D4.1 | UPV | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Adrià Rubio
A34 | Policy brief - white paper monitoring & enforcement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.1 | D4.1 | IN/EN | Virtual forum, newsletter, twitter | D4.1 | IRAP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A35 | Policy brief - white paper monitoring & enforcement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.1 | D4.1 | GR | Virtual forum, newsletter, twitter | D4.1 | KRI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A36 | Policy brief - white paper monitoring & enforcement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.1 | D4.1 | AR | Virtual forum, newsletter, twitter | D4.1 | AUB | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A37 | Policy brief - white paper monitoring & enforcement | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.1 | D4.1 | SK | Virtual forum, newsletter, twitter | D4.1 | SAZP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A38 | Policy brief - white paper scenarios | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.2 | D4.2 | IT | Virtual forum, newsletter, twitter | D4.2 | ARPAE | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A39 | Policy brief - white paper scenarios | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.2 | D4.2 | ES | Virtual forum, newsletter, twitter | D4.2 | SEI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Tania Santos
A40 | Policy brief - white paper scenarios | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.2 | D4.2 | IN/EN | Virtual forum, newsletter, twitter | D4.2 | IRAP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A41 | Policy brief - white paper scenarios | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.2 | D4.2 | GR | Virtual forum, newsletter, twitter | D4.2 | KRI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A42 | Policy brief - white paper scenarios | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.2 | D4.2 | AR | Virtual forum, newsletter, twitter | D4.2 | AUB | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A43 | Policy brief - white paper scenarios | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 4 | 4.2 | D4.2 | SK | Virtual forum, newsletter, twitter | D4.2 | SAZP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A44 | Policy brief - white paper governance | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 5 | 5.1 | D5.1 | IT | Virtual forum, newsletter, twitter | D5.1 | ARPAE | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A45 | Policy brief - white paper governance | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 5 | 5.1 | D5.1 | ES | Virtual forum, newsletter, twitter | D5.1 | UPV | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Adrià Rubio
A46 | Policy brief - white paper governance | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 5 | 5.1 | D5.1 | IN/EN | Virtual forum, newsletter, twitter | D5.1 | IRAP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A47 | Policy brief - white paper governance | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 5 | 5.1 | D5.1 | GR | Virtual forum, newsletter, twitter | D5.1 | KRI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A48 | Policy brief - white paper governance | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 5 | 5.1 | D5.1 | AR | Virtual forum, newsletter, twitter | D5.1 | AUB | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A49 | Policy brief - white paper governance | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 10 | 5 | 5.1 | D5.1 | SK | Virtual forum, newsletter, twitter | D5.1 | SAZP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A50 | Policy brief - white paper financing | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 5 | 5.2 | D5.2 | IT | Virtual forum, newsletter, twitter | D5.2 | ARPAE | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A51 | Policy brief - white paper financing | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 5 | 5.2 | D5.2 | ES | Virtual forum, newsletter, twitter | D5.2 | SEI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Tania Santos
A52 | Policy brief - white paper financing | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 5 | 5.2 | D5.2 | IN/EN | Virtual forum, newsletter, twitter | D5.2 | IRAP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A53 | Policy brief - white paper financing | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 5 | 5.2 | D5.2 | GR | Virtual forum, newsletter, twitter | D5.2 | KRI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A54 | Policy brief - white paper financing | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 5 | 5.2 | D5.2 | AR | Virtual forum, newsletter, twitter | D5.2 | AUB | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A55 | Policy brief - white paper financing | Stakehodler oriented summary of a key deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 5 | 5.2 | D5.2 | SK | Virtual forum, newsletter, twitter | D5.2 | SAZP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A56 | Policy brief - modeling suite sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 19 | 3 | 3.1 | D3.2 | IT | Virtual forum, newsletter, twitter | D3.2 | ARPAE | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A57 | Policy brief - modeling suite sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 19 | 3 | 3.1 | D3.2 | ES | Virtual forum, newsletter, twitter | D3.2 | UPV | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Adrià Rubio
A58 | Policy brief - modeling suite sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 19 | 3 | 3.1 | D3.2 | IN/EN | Virtual forum, newsletter, twitter | D3.2 | IRAP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A59 | Policy brief - modeling suite sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 19 | 3 | 3.1 | D3.2 | GR | Virtual forum, newsletter, twitter | D3.2 | KRI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A60 | Policy brief - modeling suite sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 19 | 3 | 3.1 | D3.2 | AR | Virtual forum, newsletter, twitter | D3.2 | AUB | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A61 | Policy brief - modeling suite sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 19 | 3 | 3.1 | D3.2 | SK | Virtual forum, newsletter, twitter | D3.2 | SAZP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A62 | Policy brief - water accounting & impact assessment sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 4 | 4.1 | D4.4 | IT | Virtual forum, newsletter, twitter | D4.4 | ARPAE | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A63 | Policy brief - water accounting & impact assessment sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 4 | 4.1 | D4.4 | ES | Virtual forum, newsletter, twitter | D4.4 | SEI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Tania Santos
A64 | Policy brief - water accounting & impact assessment sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 4 | 4.1 | D4.4 | IN/EN | Virtual forum, newsletter, twitter | D4.4 | IRAP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A65 | Policy brief - water accounting & impact assessment sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 4 | 4.1 | D4.4 | GR | Virtual forum, newsletter, twitter | D4.4 | KRI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A66 | Policy brief - water accounting & impact assessment sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 4 | 4.1 | D4.4 | AR | Virtual forum, newsletter, twitter | D4.4 | AUB | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A67 | Policy brief - water accounting & impact assessment sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 21 | 4 | 4.1 | D4.4 | SK | Virtual forum, newsletter, twitter | D4.4 | SAZP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A68 | Policy brief - policy notebook | Notebook produced as deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 4 | 5.1-3 | D5.3 | IT | Virtual forum, newsletter, twitter | D5.3 | ARPAE | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A69 | Policy brief - policy notebook | Notebook produced as deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 4 | 5.1-3 | D5.3 | ES | Virtual forum, newsletter, twitter | D5.3 | UPV | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Adrià Rubio
A70 | Policy brief - policy notebook | Notebook produced as deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 4 | 5.1-3 | D5.3 | IN/EN | Virtual forum, newsletter, twitter | D5.3 | IRAP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A71 | Policy brief - policy notebook | Notebook produced as deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 4 | 5.1-3 | D5.3 | GR | Virtual forum, newsletter, twitter | D5.3 | KRI | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A72 | Policy brief - policy notebook | Notebook produced as deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 4 | 5.1-3 | D5.3 | AR | Virtual forum, newsletter, twitter | D5.3 | AUB | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A73 | Policy brief - policy notebook | Notebook produced as deliverable | 50+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 4 | 5.1-3 | D5.3 | SK | Virtual forum, newsletter, twitter | D5.3 | SAZP | Translate policy brief and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A74 | Policy brief - scenarios database sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 39 | 4 | 4.2 | D4.5 | IT | Virtual forum, newsletter, twitter | D4.5 | ARPAE | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Cinzia Alessandrini
A75 | Policy brief - scenarios database sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 39 | 4 | 4.2 | D4.5 | ES | Virtual forum, newsletter, twitter | D4.5 | SEI | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Tania Santos
A76 | Policy brief - scenarios database sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 39 | 4 | 4.2 | D4.5 | IN/EN | Virtual forum, newsletter, twitter | D4.5 | IRAP | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Dinesh Kumar
A77 | Policy brief - scenarios database sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 39 | 4 | 4.2 | D4.5 | GR | Virtual forum, newsletter, twitter | D4.5 | KRI | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Marinos Kritsotakis
A78 | Policy brief - scenarios database sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 39 | 4 | 4.2 | D4.5 | AR | Virtual forum, newsletter, twitter | D4.5 | AUB | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Hadi Jaafar
A79 | Policy brief - scenarios database sourcebook | Sourcebook produced as part of a deliverable | 20+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 39 | 4 | 4.2 | D4.5 | SK | Virtual forum, newsletter, twitter | D4.5 | SAZP | ARPAE to disseminate widely the sourcebook attached to this deliverable at a EU level leveraging on our networks | Radoslav Povazan
A80 | Webinar 1 - focus on awareness - timed ahead of workshops | Webinar presenting results from a published paper to scientists and stakeholders in layman words, focusing on the relevance for labs; it will be embedded in webstival | 40+ stakeholders | Participants in meeting | 9 | 5 | TBD by CMCC | TBD by CMCC | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | WP5 | TBD by CMCC | CMCC to pick a partner to make a presentation on relevant topic to stakeholders - and to widely disseminate the event as part of the webstival (see activity: webstivals) | TBD by CMCC
A81 | Webinar 2 | Webinar presenting results from a published paper to scientists and stakeholders in layman words, focusing on the relevance for labs; it will be embedded in webstival | 40+ stakeholders | Participants in meeting | 22 | 3 | TBD by CMCC | TBD by CMCC | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | WP3 | TBD by CMCC | CMCC to pick a partner to make a presentation on relevant topic to stakeholders - and to widely disseminate the event as part of the webstival (see activity: webstivals) | TBD by CMCC
A82 | Webinar 3 | Webinar presenting results from a published paper to scientists and stakeholders in layman words, focusing on the relevance for labs; it will be embedded in webstival | 40+ stakeholders | Participants in meeting | 34 | 4 | TBD by CMCC | TBD by CMCC | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | WP4 | TBD by CMCC | CMCC to pick a partner to make a presentation on relevant topic to stakeholders - and to widely disseminate the event as part of the webstival (see activity: webstivals) | TBD by CMCC
A83 | Webinar 4 | Webinar presenting results from a published paper to scientists and stakeholders in layman words, focusing on the relevance for labs; it will be embedded in webstival | 40+ stakeholders | Participants in meeting | 46 | 2 | TBD by CMCC | TBD by CMCC | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | WP2 | TBD by CMCC | CMCC to pick a partner to make a presentation on relevant topic to stakeholders - and to widely disseminate the event as part of the webstival (see activity: webstivals) | TBD by CMCC
A84 | Newsletter 1 | Newsletter presenting main project advances in layman words to stakeholders | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 6 | 6 | 6.3 | D6.3-6 | EN | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | ARPAE to build a newsletter to summarize key dissemination materials provided by other partners (policy briefs, webinars, others) | Cinzia Alessandrini
A85 | Newsletter 2 | Newsletter presenting main project advances in layman words to stakeholders | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 12 | 6 | 6.3 | D6.3-7 | EN | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | ARPAE to build a newsletter to summarize key dissemination materials provided by other partners (policy briefs, webinars, others) | Cinzia Alessandrini
A86 | Newsletter 3 | Newsletter presenting main project advances in layman words to stakeholders | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 18 | 6 | 6.3 | D6.3-8 | EN | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | ARPAE to build a newsletter to summarize key dissemination materials provided by other partners (policy briefs, webinars, others) | Cinzia Alessandrini
A87 | Newsletter 4 | Newsletter presenting main project advances in layman words to stakeholders | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 24 | 6 | 6.3 | D6.3-9 | EN | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | ARPAE to build a newsletter to summarize key dissemination materials provided by other partners (policy briefs, webinars, others) | Cinzia Alessandrini
A88 | Newsletter 5 | Newsletter presenting main project advances in layman words to stakeholders | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 30 | 6 | 6.3 | D6.3-10 | EN | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | ARPAE to build a newsletter to summarize key dissemination materials provided by other partners (policy briefs, webinars, others) | Cinzia Alessandrini
A89 | Newsletter 6 | Newsletter presenting main project advances in layman words to stakeholders | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 36 | 6 | 6.3 | D6.3-11 | EN | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | ARPAE to build a newsletter to summarize key dissemination materials provided by other partners (policy briefs, webinars, others) | Cinzia Alessandrini
A90 | Newsletter 7 | Newsletter presenting main project advances in layman words to stakeholders | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 42 | 6 | 6.3 | D6.3-12 | EN | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | ARPAE to build a newsletter to summarize key dissemination materials provided by other partners (policy briefs, webinars, others) | Cinzia Alessandrini
A91 | Newsletter 8 | Newsletter presenting main project advances in layman words to stakeholders | 100+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 6 | 6.3 | D6.3-13 | EN | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | ARPAE to build a newsletter to summarize key dissemination materials provided by other partners (policy briefs, webinars, others) | Cinzia Alessandrini
A92 | Paper in Nature/Science | Key scientific outcome focused on modeling efforts | 500+ scientists | N. reads from Nature/Science website | 34 | 3 | 3.1-3 | D3.3 | EN | Nature/Science website, virtual forum, twitter, newsletter | WP3 | UU | Initiate the coordination of partners to produce a paper in Nature/Science based on outputs from TRANSCEND | Giuliano di Baldassarre
A93 | Webstival 1, featuring webinar 1 and training 1 - focus on awareness - timed ahead of workshops | Major event with stakeholders | 60+ stakeholders | Participants in meeting | 9 | 6 | 6.3 | D6.3-6 | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | All | CMCC | Organize webstival | Mauro Buonocuore
A94 | Webstival 2, featuring webinar 2 and training 2 | Major event with stakeholders | 60+ stakeholders | Participants in meeting | 22 | 6 | 6.3 | D6.3-6 | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | All | CMCC | Organize webstival | Mauro Buonocuore
A95 | Webstival 3, featuring webinar 3 and training 3 | Major event with stakeholders | 60+ stakeholders | Participants in meeting | 34 | 6 | 6.3 | D6.3-6 | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | All | CMCC | Organize webstival | Mauro Buonocuore
A96 | Webstival 4, featuring webinar 4 and training 4 | Major event with stakeholders | 60+ stakeholders | Participants in meeting | 46 | 6 | 6.3 | D6.3-6 | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | All | CMCC | Organize webstival | Mauro Buonocuore
A97 | Newsletter 1 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 6 | 6.3 | D6.3-6 | IT | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A98 | Newsletter 1 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 6 | 6.3 | D6.3-6 | ES | Virtual Forum, twitter, email to knowledge networks | All | SEI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Tania Santos
A99 | Newsletter 1 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 6 | 6.3 | D6.3-6 | IN/EN | Virtual Forum, twitter, email to knowledge networks | All | IRAP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A100 | Newsletter 1 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 6 | 6.3 | D6.3-6 | GR | Virtual Forum, twitter, email to knowledge networks | All | KRI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A101 | Newsletter 1 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 6 | 6.3 | D6.3-6 | AR | Virtual Forum, twitter, email to knowledge networks | All | AUB | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A102 | Newsletter 1 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 8 | 6 | 6.3 | D6.3-6 | SK | Virtual Forum, twitter, email to knowledge networks | All | SAZP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A103 | Newsletter 2 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 14 | 6 | 6.3 | D6.3-6 | IT | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A104 | Newsletter 2 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 14 | 6 | 6.3 | D6.3-6 | ES | Virtual Forum, twitter, email to knowledge networks | All | UPV | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Adrià Rubio
A105 | Newsletter 2 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 14 | 6 | 6.3 | D6.3-6 | IN/EN | Virtual Forum, twitter, email to knowledge networks | All | IRAP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A106 | Newsletter 2 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 14 | 6 | 6.3 | D6.3-6 | GR | Virtual Forum, twitter, email to knowledge networks | All | KRI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A107 | Newsletter 2 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 14 | 6 | 6.3 | D6.3-6 | AR | Virtual Forum, twitter, email to knowledge networks | All | AUB | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A108 | Newsletter 2 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 14 | 6 | 6.3 | D6.3-6 | SK | Virtual Forum, twitter, email to knowledge networks | All | SAZP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A109 | Newsletter 3 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 20 | 6 | 6.3 | D6.3-6 | IT | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A110 | Newsletter 3 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 20 | 6 | 6.3 | D6.3-6 | ES | Virtual Forum, twitter, email to knowledge networks | All | SEI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Tania Santos
A111 | Newsletter 3 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 20 | 6 | 6.3 | D6.3-6 | IN/EN | Virtual Forum, twitter, email to knowledge networks | All | IRAP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A112 | Newsletter 3 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 20 | 6 | 6.3 | D6.3-6 | GR | Virtual Forum, twitter, email to knowledge networks | All | KRI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A113 | Newsletter 3 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 20 | 6 | 6.3 | D6.3-6 | AR | Virtual Forum, twitter, email to knowledge networks | All | AUB | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A114 | Newsletter 3 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 20 | 6 | 6.3 | D6.3-6 | SK | Virtual Forum, twitter, email to knowledge networks | All | SAZP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A115 | Newsletter 4 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 26 | 6 | 6.3 | D6.3-6 | IT | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A116 | Newsletter 4 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 26 | 6 | 6.3 | D6.3-6 | ES | Virtual Forum, twitter, email to knowledge networks | All | UPV | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Adrià Rubio
A117 | Newsletter 4 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 26 | 6 | 6.3 | D6.3-6 | IN/EN | Virtual Forum, twitter, email to knowledge networks | All | IRAP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A118 | Newsletter 4 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 26 | 6 | 6.3 | D6.3-6 | GR | Virtual Forum, twitter, email to knowledge networks | All | KRI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A119 | Newsletter 4 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 26 | 6 | 6.3 | D6.3-6 | AR | Virtual Forum, twitter, email to knowledge networks | All | AUB | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A120 | Newsletter 4 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 26 | 6 | 6.3 | D6.3-6 | SK | Virtual Forum, twitter, email to knowledge networks | All | SAZP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A121 | Newsletter 5 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 32 | 6 | 6.3 | D6.3-6 | IT | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A122 | Newsletter 5 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 32 | 6 | 6.3 | D6.3-6 | ES | Virtual Forum, twitter, email to knowledge networks | All | SEI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Tania Santos
A123 | Newsletter 5 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 32 | 6 | 6.3 | D6.3-6 | IN/EN | Virtual Forum, twitter, email to knowledge networks | All | IRAP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A124 | Newsletter 5 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 32 | 6 | 6.3 | D6.3-6 | GR | Virtual Forum, twitter, email to knowledge networks | All | KRI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A125 | Newsletter 5 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 32 | 6 | 6.3 | D6.3-6 | AR | Virtual Forum, twitter, email to knowledge networks | All | AUB | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A126 | Newsletter 5 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 32 | 6 | 6.3 | D6.3-6 | SK | Virtual Forum, twitter, email to knowledge networks | All | SAZP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A127 | Newsletter 6 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 38 | 6 | 6.3 | D6.3-6 | IT | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A128 | Newsletter 6 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 38 | 6 | 6.3 | D6.3-6 | ES | Virtual Forum, twitter, email to knowledge networks | All | UPV | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Adrià Rubio
A129 | Newsletter 6 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 38 | 6 | 6.3 | D6.3-6 | IN/EN | Virtual Forum, twitter, email to knowledge networks | All | IRAP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A130 | Newsletter 6 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 38 | 6 | 6.3 | D6.3-6 | GR | Virtual Forum, twitter, email to knowledge networks | All | KRI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A131 | Newsletter 6 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 38 | 6 | 6.3 | D6.3-6 | AR | Virtual Forum, twitter, email to knowledge networks | All | AUB | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A132 | Newsletter 6 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 38 | 6 | 6.3 | D6.3-6 | SK | Virtual Forum, twitter, email to knowledge networks | All | SAZP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A133 | Newsletter 7 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 44 | 6 | 6.3 | D6.3-6 | IT | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A134 | Newsletter 7 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 44 | 6 | 6.3 | D6.3-6 | ES | Virtual Forum, twitter, email to knowledge networks | All | SEI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Tania Santos
A135 | Newsletter 7 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 44 | 6 | 6.3 | D6.3-6 | IN/EN | Virtual Forum, twitter, email to knowledge networks | All | IRAP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A136 | Newsletter 7 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 44 | 6 | 6.3 | D6.3-6 | GR | Virtual Forum, twitter, email to knowledge networks | All | KRI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A137 | Newsletter 7 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 44 | 6 | 6.3 | D6.3-6 | AR | Virtual Forum, twitter, email to knowledge networks | All | AUB | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A138 | Newsletter 7 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 44 | 6 | 6.3 | D6.3-6 | SK | Virtual Forum, twitter, email to knowledge networks | All | SAZP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A139 | Newsletter 8 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 6 | 6.3 | D6.3-6 | IT | Virtual Forum, twitter, email to knowledge networks | All | ARPAE | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Cinzia Alessandrini
A140 | Newsletter 8 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 6 | 6.3 | D6.3-6 | ES | Virtual Forum, twitter, email to knowledge networks | All | UPV | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Adrià Rubio
A141 | Newsletter 8 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 6 | 6.3 | D6.3-6 | IN/EN | Virtual Forum, twitter, email to knowledge networks | All | IRAP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Dinesh Kumar
A142 | Newsletter 8 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 6 | 6.3 | D6.3-6 | GR | Virtual Forum, twitter, email to knowledge networks | All | KRI | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Marinos Kritsotakis
A143 | Newsletter 8 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 6 | 6.3 | D6.3-6 | AR | Virtual Forum, twitter, email to knowledge networks | All | AUB | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Hadi Jaafar
A144 | Newsletter 8 | Newsletter presenting main project advances in layman words to stakeholders | 30+ stakeholders | Downloads from Virtual forum, other verifiable indicators (e.g. "read" emails) | 48 | 6 | 6.3 | D6.3-6 | SK | Virtual Forum, twitter, email to knowledge networks | All | SAZP | Translate newsletter and disseminate in the network in the relevant lab / and possibly at a national level and in legacy labs connected to the living lab (using same language) | Radoslav Povazan
A145 | Stakeholder training event 1 - Focus on awareness - it should be timed ahead of workshops (i.e., in early September) | Training to stakeholders, focusing on policy makers; it will be embedded in webstival | 40+ stakeholders | Participants in meeting | 9 | 5 | 2023-02-01 | 1 | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | WP5 | TBD by CMCC | CMCC to pick a partner to develop an initial training that raises awareness - and to widely disseminate the event as part of the webstival (see activity: webstivals) | TBD by CMCC
A146 | Stakeholder training event 2 | Training to stakeholders, focusing on policy makers; it will be embedded in webstival | 40+ stakeholders | Participants in meeting | 22 | 3 | TBD by CMCC | TBD by CMCC | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | WP3 | TBD by CMCC | CMCC to pick a partner to make a training on relevant topic to stakeholders - and to widely disseminate the event as part of the webstival (see activity: webstivals) | TBD by CMCC
A147 | Stakeholder training event 3 | Training to stakeholders, focusing on policy makers; it will be embedded in webstival | 40+ stakeholders | Participants in meeting | 34 | 4 | TBD by CMCC | TBD by CMCC | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | WP4 | TBD by CMCC | CMCC to pick a partner to make a training on relevant topic to stakeholders - and to widely disseminate the event as part of the webstival (see activity: webstivals) | TBD by CMCC
A148 | Stakeholder training event 4 | Training to stakeholders, focusing on policy makers; it will be embedded in webstival | 40+ stakeholders | Participants in meeting | 46 | 2 | TBD by CMCC | TBD by CMCC | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | WP2 | TBD by CMCC | CMCC to pick a partner to make a training on relevant topic to stakeholders - and to widely disseminate the event as part of the webstival (see activity: webstivals) | TBD by CMCC
A149 | Stakeholder training event 5 | Training to stakeholders embedded in activities of Climate KIC | 15+ stakeholders | Participants in meeting | 44 | 6 | 6.3 | D6.3-6 | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | All | CMCC | CMCC to organize a wide-reaching training event in coordination with Climate KIC ntwork | TBD by CMCC
A150 | Stakeholder training event 6 | Training to stakeholders in the IT lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | IT | In person | All | CMCC | Organize a session to train stakeholders back-to-back the workshop in that lab | Jaroslav Mysiak
A151 | Stakeholder training event 7 | Training to stakeholders in the ES - Júcar lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | ES | In person | All | UPV | Organize a session to train stakeholders back-to-back the workshop in that lab | Manuel Pulido Velázquez
A152 | Stakeholder training event 8 | Training to stakeholders in the IN-Mahanadi lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | IN/EN | In person | All | IRAP | Organize a session to train stakeholders back-to-back the workshop in that lab | Dinesh Kumar
A153 | Stakeholder training event 9 | Training to stakeholders in the GR lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | GR | In person | All | SEVEN | Organize a session to train stakeholders back-to-back the workshop in that lab | Maggie Kossida
A154 | Stakeholder training event 10 | Training to stakeholders in the Orontes lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | AR | In person | All | AUB | Organize a session to train stakeholders back-to-back the workshop in that lab | Hadi Jaafar
A155 | Stakeholder training event 11 | Training to stakeholders in the Nitra lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | SK | In person | All | SAZP | Organize a session to train stakeholders back-to-back the workshop in that lab | Radoslav Povazan
A156 | Stakeholder training event 12 | Training to stakeholders in the Caplina-Mauri-Desaguadero lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | ES | In person | All | SEI | Organize a session to train stakeholders back-to-back the workshop in that lab | Tania Santos
A157 | Stakeholder training event 13 | Training to stakeholders in the IT lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | IT | In person | All | CMCC | Organize a session to train stakeholders back-to-back the workshop in that lab | Cinzia Alessandrini
A158 | Stakeholder training event 14 | Training to stakeholders in the ES - Júcar lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | ES | In person | All | UPV | Organize a session to train stakeholders back-to-back the workshop in that lab | Manuel Pulido Velázquez
A159 | Stakeholder training event 15 | Training to stakeholders in the IN-Mahanadi lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | IN/EN | In person | All | IRAP | Organize a session to train stakeholders back-to-back the workshop in that lab | Dinesh Kumar
A160 | Stakeholder training event 16 | Training to stakeholders in the GR lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | GR | In person | All | SEVEN | Organize a session to train stakeholders back-to-back the workshop in that lab | Maggie Kossida
A161 | Stakeholder training event 17 | Training to stakeholders in the Orontes lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | AR | In person | All | AUB | Organize a session to train stakeholders back-to-back the workshop in that lab | Hadi Jaafar
A162 | Stakeholder training event 18 | Training to stakeholders in the Nitra lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | SK | In person | All | SAZP | Organize a session to train stakeholders back-to-back the workshop in that lab | Radoslav Povazan
A163 | Stakeholder training event 19 | Training to stakeholders in the Caplina-Mauri-Desaguadero lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | ES | In person | All | SEI | Organize a session to train stakeholders back-to-back the workshop in that lab | Tania Santos
A164 | Stakeholder training event 20 | Training to stakeholders in the IT lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | IT | In person | All | CMCC | Organize a session to train stakeholders back-to-back the workshop in that lab | Cinzia Alessandrini
A165 | Stakeholder training event 21 | Training to stakeholders in the ES - Júcar lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | ES | In person | All | UPV | Organize a session to train stakeholders back-to-back the workshop in that lab | Manuel Pulido Velázquez
A166 | Stakeholder training event 22 | Training to stakeholders in the IN-Mahanadi lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | IN/EN | In person | All | IRAP | Organize a session to train stakeholders back-to-back the workshop in that lab | Dinesh Kumar
A167 | Stakeholder training event 23 | Training to stakeholders in the GR lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | GR | In person | All | SEVEN | Organize a session to train stakeholders back-to-back the workshop in that lab | Maggie Kossida
A168 | Stakeholder training event 24 | Training to stakeholders in the Orontes lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | AR | In person | All | AUB | Organize a session to train stakeholders back-to-back the workshop in that lab | Hadi Jaafar
A169 | Stakeholder training event 25 | Training to stakeholders in the Nitra lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | SK | In person | All | SAZP | Organize a session to train stakeholders back-to-back the workshop in that lab | Radoslav Povazan
A170 | Stakeholder training event 26 | Training to stakeholders in the Caplina-Mauri-Desaguadero lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | ES | In person | All | SEI | Organize a session to train stakeholders back-to-back the workshop in that lab | Tania Santos
A171 | Stakeholder training event 27 | Training to stakeholders in the IT lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | IT | In person | All | CMCC | Organize a session to train stakeholders back-to-back the workshop in that lab | Jaroslav Mysiak
A172 | Stakeholder training event 28 | Training to stakeholders in the ES - Júcar lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | ES | In person | All | UPV | Organize a session to train stakeholders back-to-back the workshop in that lab | Manuel Pulido Velázquez
A173 | Stakeholder training event 29 | Training to stakeholders in the IN-Mahanadi lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | IN/EN | In person | All | IRAP | Organize a session to train stakeholders back-to-back the workshop in that lab | Dinesh Kumar
A174 | Stakeholder training event 30 | Training to stakeholders in the GR lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | GR | In person | All | SEVEN | Organize a session to train stakeholders back-to-back the workshop in that lab | Maggie Kossida
A175 | Stakeholder training event 31 | Training to stakeholders in the Orontes lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | AR | In person | All | AUB | Organize a session to train stakeholders back-to-back the workshop in that lab | Hadi Jaafar
A176 | Stakeholder training event 32 | Training to stakeholders in the Nitra lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | SK | In person | All | SAZP | Organize a session to train stakeholders back-to-back the workshop in that lab | Radoslav Povazan
A177 | Stakeholder training event 33 | Training to stakeholders in the Caplina-Mauri-Desaguadero lab; it will be embedded in the lab workshop | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | ES | In person | All | SEI | Organize a session to train stakeholders back-to-back the workshop in that lab | Tania Santos
A178 | Stakeholder training event 34 | Training to stakeholders embedded in activities of PRIMA, UN’s WASAG, SWIM H2020 and/or DG NEAR WES | 40+ stakeholders | Participants in meeting | 24 | 6 | 6.3 | D6.3-6 | EN | Zoom/Gmeet embedded in virtual forum, disseminated to network, recorded and uploaded to Virtual forum | All | USAL | USAL to organize a wide-reaching training event in coordination with PRIMA, UN’s WASAG, SWIM H2020 and/or DG NEAR WES | C. Dionisio Pérez-Blanco
A179 | Summer/winter school 1 | Summer/winter school | 20+ PhD students | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | EN | In person | All | UU | UU to organize a summer/winter school, if possible in collaboration with events already arranged by the institution in the context of other activities/projects | Giuliano di Baldassarre
A180 | Summer/winter school 2 | Summer/winter school | 30+ PhD students | Participants in meeting | 42 | 6 | 6.3 | D6.3-6 | EN | In person | All | SEI | UU to organize a summer/winter school, if possible in collaboration with events already arranged by the institution in the context of other activities/projects | Tania Santos
A181 | Flagship report 1 | Contribution to flagship report using outputs from TRANSCEND (DRMKC, GAR, other reports) | 1 flagship report | Publication acknowledging contribution of partner, contribution is based on TRANSCEND | 36 | 6 | 6.3 | D6.3-6 | EN | In person | All | CMCC | Contribute to a flagship report leveraging on TRANSCEND outputs | Jaroslav Mysiak
A182 | Flagship report 2 | Contribution to flagship report using outputs from TRANSCEND (DRMKC, GAR, other reports) | 1 flagship report | Publication acknowledging contribution of partner, contribution is based on TRANSCEND | 36 | 6 | 6.3 | D6.3-6 | EN | In person | All | FTC | Contribute to a flagship report leveraging on TRANSCEND outputs | Guido Schmidt
A183 | Flagship report 3 | Contribution to flagship report using outputs from TRANSCEND (DRMKC, GAR, other reports) | 1 flagship report | Publication acknowledging contribution of partner, contribution is based on TRANSCEND | 36 | 6 | 6.3 | D6.3-6 | EN | In person | All | SEVEN | Contribute to a flagship report leveraging on TRANSCEND outputs | Maggie Kossida
A184 | Virtual forum developed | Website ready | project website ready, can be readily used in phone navigators | Online | 4 | 6 | 6.3 | D6.3-6 | EN | In person | All | USAL | Contribute to a flagship report leveraging on TRANSCEND outputs | Héctor González-López
A185 | Workshop Reno lab 1 | Scene setting, momentum building; research gaps, challenges and uncertainties; exploratory co-design and co-development. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | IT | In person | All | ARPAE | Organize workshop in line with objectives set in the DoW and GA | Cinzia Alessandrini
A186 | Workshop Júcar lab 1 | Scene setting, momentum building; research gaps, challenges and uncertainties; exploratory co-design and co-development. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | ES | In person | All | UPV | Organize workshop in line with objectives set in the DoW and GA | Manuel Pulido Velázquez
A187 | Workshop Mahanadi lab 1 | Scene setting, momentum building; research gaps, challenges and uncertainties; exploratory co-design and co-development. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | IN/EN | In person | All | IRAP | Organize workshop in line with objectives set in the DoW and GA | Dinesh Kumar
A188 | Workshop Tympaki lab 1 | Scene setting, momentum building; research gaps, challenges and uncertainties; exploratory co-design and co-development. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | GR | In person | All | KRI | Organize workshop in line with objectives set in the DoW and GA | Marinos Kritsotakis
A189 | Workshop Orontes lab 1 | Scene setting, momentum building; research gaps, challenges and uncertainties; exploratory co-design and co-development. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | AR | In person | All | AUB | Organize workshop in line with objectives set in the DoW and GA | Hadi Jaafar
A190 | Workshop Nitra lab 1 | Scene setting, momentum building; research gaps, challenges and uncertainties; exploratory co-design and co-development. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | SK | In person | All | SAZP | Organize workshop in line with objectives set in the DoW and GA | Radoslav Povazan
A191 | Workshop Caplina-Mauri-Desaguadero lab 1 | Scene setting, momentum building; research gaps, challenges and uncertainties; exploratory co-design and co-development. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 8 | 6 | 6.3 | D6.3-6 | ES | In person | All | SEI | Organize workshop in line with objectives set in the DoW and GA | Tania Santos
A192 | Workshop Reno lab 2 | Scenathon; co-evaluation; revision of TAP, scenarios and modeling suite (iterative stock-taking process). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | IT | In person | All | ARPAE | Organize workshop in line with objectives set in the DoW and GA | Cinzia Alessandrini
A193 | Workshop Júcar lab 2 | Scenathon; co-evaluation; revision of TAP, scenarios and modeling suite (iterative stock-taking process). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | ES | In person | All | UPV | Organize workshop in line with objectives set in the DoW and GA | Manuel Pulido Velázquez
A194 | Workshop Mahanadi lab 2 | Scenathon; co-evaluation; revision of TAP, scenarios and modeling suite (iterative stock-taking process). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | IN/EN | In person | All | IRAP | Organize workshop in line with objectives set in the DoW and GA | Dinesh Kumar
A195 | Workshop Tympaki lab 2 | Scenathon; co-evaluation; revision of TAP, scenarios and modeling suite (iterative stock-taking process). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | GR | In person | All | KRI | Organize workshop in line with objectives set in the DoW and GA | Marinos Kritsotakis
A196 | Workshop Orontes lab 2 | Scenathon; co-evaluation; revision of TAP, scenarios and modeling suite (iterative stock-taking process). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | AR | In person | All | AUB | Organize workshop in line with objectives set in the DoW and GA | Hadi Jaafar
A197 | Workshop Nitra lab 2 | Scenathon; co-evaluation; revision of TAP, scenarios and modeling suite (iterative stock-taking process). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | SK | In person | All | SAZP | Organize workshop in line with objectives set in the DoW and GA | Radoslav Povazan
A198 | Workshop Caplina-Mauri-Desaguadero lab 2 | Scenathon; co-evaluation; revision of TAP, scenarios and modeling suite (iterative stock-taking process). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 19 | 6 | 6.3 | D6.3-6 | ES | In person | All | SEI | Organize workshop in line with objectives set in the DoW and GA | Tania Santos
A199 | Workshop Reno lab 3 | Scenathon; exploratory co-identification; revision of TAP and scenarios, new iteration(s). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | IT | In person | All | ARPAE | Organize workshop in line with objectives set in the DoW and GA | Cinzia Alessandrini
A200 | Workshop Júcar lab 3 | Scenathon; exploratory co-identification; revision of TAP and scenarios, new iteration(s). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | ES | In person | All | UPV | Organize workshop in line with objectives set in the DoW and GA | Manuel Pulido Velázquez
A201 | Workshop Mahanadi lab 3 | Scenathon; exploratory co-identification; revision of TAP and scenarios, new iteration(s). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | IN/EN | In person | All | IRAP | Organize workshop in line with objectives set in the DoW and GA | Dinesh Kumar
A202 | Workshop Tympaki lab 3 | Scenathon; exploratory co-identification; revision of TAP and scenarios, new iteration(s). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | GR | In person | All | KRI | Organize workshop in line with objectives set in the DoW and GA | Marinos Kritsotakis
A203 | Workshop Orontes lab 3 | Scenathon; exploratory co-identification; revision of TAP and scenarios, new iteration(s). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | AR | In person | All | AUB | Organize workshop in line with objectives set in the DoW and GA | Hadi Jaafar
A204 | Workshop Nitra lab 3 | Scenathon; exploratory co-identification; revision of TAP and scenarios, new iteration(s). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | SK | In person | All | SAZP | Organize workshop in line with objectives set in the DoW and GA | Radoslav Povazan
A205 | Workshop Caplina-Mauri-Desaguadero lab 3 | Scenathon; exploratory co-identification; revision of TAP and scenarios, new iteration(s). Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 30 | 6 | 6.3 | D6.3-6 | ES | In person | All | SEI | Organize workshop in line with objectives set in the DoW and GA | Tania Santos
A206 | Workshop Reno lab 4 | Presentation of detailed modeling results in scenathon, co-identification; plan for co-implementation of selected TAP in labs. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | IT | In person | All | ARPAE | Organize workshop in line with objectives set in the DoW and GA | Cinzia Alessandrini
A207 | Workshop Júcar lab 4 | Presentation of detailed modeling results in scenathon, co-identification; plan for co-implementation of selected TAP in labs. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | ES | In person | All | UPV | Organize workshop in line with objectives set in the DoW and GA | Manuel Pulido Velázquez
A208 | Workshop Mahanadi lab 4 | Presentation of detailed modeling results in scenathon, co-identification; plan for co-implementation of selected TAP in labs. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | IN/EN | In person | All | IRAP | Organize workshop in line with objectives set in the DoW and GA | Dinesh Kumar
A209 | Workshop Tympaki lab 4 | Presentation of detailed modeling results in scenathon, co-identification; plan for co-implementation of selected TAP in labs. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | GR | In person | All | KRI | Organize workshop in line with objectives set in the DoW and GA | Marinos Kritsotakis
A210 | Workshop Orontes lab 4 | Presentation of detailed modeling results in scenathon, co-identification; plan for co-implementation of selected TAP in labs. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | AR | In person | All | AUB | Organize workshop in line with objectives set in the DoW and GA | Hadi Jaafar
A211 | Workshop Nitra lab 4 | Presentation of detailed modeling results in scenathon, co-identification; plan for co-implementation of selected TAP in labs. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | SK | In person | All | SAZP | Organize workshop in line with objectives set in the DoW and GA | Radoslav Povazan
A212 | Workshop Caplina-Mauri-Desaguadero lab 4 | Presentation of detailed modeling results in scenathon, co-identification; plan for co-implementation of selected TAP in labs. Participants: local stakeholders | 15+ stakeholders | Participants in meeting | 36 | 6 | 6.3 | D6.3-6 | ES | In person | All | SEI | Organize workshop in line with objectives set in the DoW and GA | Tania Santos
A213 | Int'l workshop 1 | Scenathon; cross-fertilization; collective identification of gaps and challenges, and TAP with high potential. Participants: int’l network board, other key stakeholders. | 35+ stakeholders | Participants in meeting | 25 | 6 | 6.3 | D6.3-6 | EN | In person | All | CMCC | Organize workshop in line with objectives set in the DoW and GA | Jaroslav Mysiak
A214 | Int'l workshop 2 | Collective assessment of outputs and co-implementation plans; barriers & reform options for upscaling and legacy; define inspiration labs. Participants: int’l network board, other key stakeholders | 35+ stakeholders | Participants in meeting | 42 | 6 | 6.3 | D6.3-6 | EN | In person | All | UPV | Organize workshop in line with objectives set in the DoW and GA | Manuel Pulido Velázquez
A215 | Twitters | Original entries leveraging on diss & comm activities | 48+ posts, 300+ reposts | N. of individual posts | 48 | 6 | 6.3 | D6.3-6 | EN | Twitter | All | ARPAE | Disseminate other activities | Cinzia Alessandrini
A216 | Facebook posts | Original entries leveraging on diss & comm activities | 48+ posts, 300+ reposts | N. of individual posts | 48 | 6 | 6.3 | D6.3-6 | EN | Facebook | All | ARPAE | Disseminate other activities | Cinzia Alessandrini
A217 | Video 1 | Original video - scribble or other format | 200+ views | Youtube views | 8 | 6 | 6.3 | D6.3-6 | EN | Youtube, embedded in virtual forum | All | USAL | Produce a video on main objectives and results of project | C. Dionisio Pérez-Blanco
A218 | Video 2 | Original video - scribble or other format | 200+ views | Youtube views | 24 | 6 | 6.3 | D6.3-6 | EN | Youtube, embedded in virtual forum | All | USAL | Produce a video on main objectives and results of project | C. Dionisio Pérez-Blanco
A219 | Video 3 | Original video - scribble or other format | 200+ views | Youtube views | 46 | 6 | 6.3 | D6.3-6 | EN | Youtube, embedded in virtual forum | All | USAL | Produce a video on main objectives and results of project | C. Dionisio Pérez-Blanco
A220 | Outreach 1 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 12 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | USAL | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A221 | Outreach 2 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 12 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | CMCC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A222 | Outreach 3 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 12 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UU | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A223 | Outreach 4 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 12 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | FTC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A224 | Outreach 5 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 12 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UPV | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A225 | Outreach 6 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 12 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEI | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A226 | Outreach 7 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 12 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | ARPAE | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A227 | Outreach 8 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 12 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEVEN | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A228 | Outreach 9 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 12 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | AUB | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A229 | Outreach 10 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 24 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | USAL | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A230 | Outreach 11 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 24 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | CMCC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A231 | Outreach 12 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 24 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UU | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A232 | Outreach 13 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 24 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | FTC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A233 | Outreach 14 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 24 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UPV | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A234 | Outreach 15 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 24 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEI | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A235 | Outreach 16 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 24 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | ARPAE | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A236 | Outreach 17 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 24 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEVEN | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A237 | Outreach 18 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 24 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | AUB | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A238 | Outreach 19 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 36 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | USAL | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A239 | Outreach 20 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 36 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | CMCC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A240 | Outreach 21 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 36 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UU | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A241 | Outreach 22 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 36 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | FTC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A242 | Outreach 23 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 36 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UPV | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A243 | Outreach 24 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 36 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEI | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A244 | Outreach 25 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 36 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | ARPAE | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A245 | Outreach 26 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 36 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEVEN | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A246 | Outreach 27 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 36 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | AUB | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A247 | Outreach 28 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | USAL | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A248 | Outreach 29 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | CMCC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A249 | Outreach 30 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UU | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A250 | Outreach 31 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | FTC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A251 | Outreach 32 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UPV | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A252 | Outreach 33 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEI | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A253 | Outreach 34 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | ARPAE | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A254 | Outreach 35 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEVEN | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A255 | Outreach 36 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | AUB | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A256 | Outreach 37 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 46 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | USAL | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A257 | Outreach 38 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 46 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | CMCC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A258 | Outreach 39 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 46 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UU | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A259 | Outreach 40 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 46 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | FTC | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A260 | Outreach 41 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 46 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UPV | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A261 | Outreach 42 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 46 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEI | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A262 | Outreach 43 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 46 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | ARPAE | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A263 | Outreach 44 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 46 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | SEVEN | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A264 | Outreach 45 | Participation in session(s) of outreach event organized by third parties | 1+ presentation | Ppt, agenda | 46 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | AUB | Participate and conduct outreach activity in relevant event, see e.g. table 2.2b in DoW
A265 | Outreach 46 | Organize dedicate session to TRANSCEND in key outreach event | 1+ presentation | Ppt, agenda | 30 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UU | Organize outreach activity in relevant events, see e.g. table 2.2b in DoW
A266 | Outreach 47 | Organize dedicate session to TRANSCEND in key outreach event | 1+ presentation | Ppt, agenda | 40 | 6 | 6.3 | D6.3-6 | EN | Virtual forum | All | UoM | Organize outreach activity in relevant events, see e.g. table 2.2b in DoW

## Sheet2
Regulators: river basin authority, environmental agency, or equivalent body managing water resources | Regulators: EU and regional to national governments
● 28 Local workshops, 2 international workshops | ● 28 Local workshops, 2 international workshops
● Virtual Forum (website, mobile app) | ● Virtual Forum (website, mobile app)
● 70+ Technical and foresight meetings | ● 70+ Technical and foresight meetings
● 34 Training events (in workshops & webstivals) | ● 34 Training events (in workshops & webstivals)
● 28 Newsletter, 7 brochure and leaflets (multilingual) | ● 28 Newsletter, 7 brochure and leaflets (multilingual)
● Twitter, Facebook and other social media | ● Twitter, Facebook and other social media
● 3 Video presentations (scribble) | ● 3 Video presentations (scribble)
● 12+ Webinars | ● 12+ Press releases in (local) newspapers
● 30 Policy briefs ahead of workshops | ● 3 Open data sets
● All project deliverables | ● 30 Policy briefs ahead of workshops
● 40+ Scientific papers | ● All project deliverables
● 45+ Outreach events, 4 webstivals | ● 45+ Outreach events, 4 webstivals
● 3 Open data sets | ● Online catalogue of TRANSCEND-enabled services
● Portals – FAO Aquastat, WaPOR, EEA, Climate Adapt
● Online catalogue of TRANSCEND-enabled services
Academia and research organizations | Utilities, industry and users’ associations
● 28 Local workshops, 2 international workshops | ● 28 Local workshops, 2 international workshops
● Virtual Forum (website, mobile app) | ● Virtual Forum (website, mobile app)
● 2 summer/winter schools | ● 34 Training events (in workshops & webstivals)
● 28 Newsletter | ● 28 Newsletter
● All Deliverables | ● 3+ Targeted brochures, e.g. COPA-COGECA
● 30 Policy briefs ahead of workshops | ● Twitter, Facebook and other social media
● 12+ Webinars | ● 3 Video presentations (scribble)
● 40+ Scientific papers | ● 30 Policy briefs ahead of workshops
● 45+ Outreach events, 4 webstivals | ● 45+ Outreach events, 4 webstivals
● 3 Open data sets | ● 3 Open data sets
● Portals – FAO Aquastat, WaPOR, EEA, Climate Adapt | ● Portals – Water Risk Filter, EEA, Climate Adapt
● 15+ Staff exchanges | ● Online catalogue of TRANSCEND services
Civil society organizations | General public
● 28 Local workshops, 2 international workshops | ● 14 Local citizen panel meetings, 1 int’l meeting
● Virtual Forum (website, mobile app) | ● Virtual Forum (website, mobile app)
● 3 Video presentations (scribble) | ● 28 Newsletter, blog, brochure
● 28 Newsletter | ● 3 Video presentations (scribble)
● Twitter, Facebook and other social media | ● Twitter, Facebook and other social media
● 30 Policy briefs ahead of workshops | ● 14+ Press releases in (local) newspapers
● 45+ outreach events, 4 webstivals | ● Portals – Water Risk Filter, EEA, Climate Adapt
● Science-society events (e.g. Researchers’ Night) | ● 14+ Citizen science events (researchers’ night)
● Portals – Water Risk Filter, EEA, Climate Adapt | ● 4 webstivals